Usability Test Guide

EP Implementation

Document properties

| Status | Date | Document version | Last modified on | Approval |
| --- | --- | --- | --- | --- |
| In process/Released | 7.31.2026 | Version 1.0 |  |  |

Change History

| Subject | Chapter | Date | Author |
| --- | --- | --- | --- |

1	About this document	4

2	Usability Test	4

2.1	What does “usability” mean?	4

2.2	Goals of the Usability Test	4

2.3	Usability Test vs. Usability Review?	4

2.4	Effort	5

2.5	Time frame	5

3	Planning the Usability Tests	5

3.1	Prerequisites	5

3.2	Kick-off meeting for the Usability Test	6

3.3	Task descriptions	6

3.4	Audience	6

4	Conducting the Usability Test	7

4.1	Introduction (15’)	7

4.2	Test Situation (30’-60’)	7

4.2.1	Deliberately reduce user support	7

4.2.2	Taking notes	8

4.3	Debriefing (30’)	8

5	Analyzing the Usability Test’s Results	9

5.1	Gathering the data	9

5.2	Making sense of the data	9

5.2.1	Usability heuristics	9

5.3	Communicating suggestions for improvement	9

6	Appendix	10

6.1	Consent for video taping (English/German)	10

# About this document

This document gives a brief description of the aims of the usability test procedure as well as how to prepare, conduct, and wrap up the actual usability test. The procedure described follows the standards established within the SAP Portals PSO EMEA’s UID team. The document is meant as an accelerator for Portal implementation projects and will help specialists with the proper training to do good usability testing. It is not meant as a general introduction into the field of usability evaluation methods and cannot replace training.

The document is split in six parts: First you are given a brief overview on what a usability test is about. Then the processes of planning and conducting the test and making sense of the data are described. In the appendix you’ll find some helpful documents.

# Usability Test

This section provides you with a general overview of what a usability test is about, what goals can be achieved through conducting a usability test, and what effort and what time frames need to be considered.

## What does “usability” mean?

According to ISO 9241-11, usability is defined as the “extent to which a product can be used by specified users to achieve specified goals with effectiveness, efficiency and satisfaction in a specified context of use”. It is important to stress that there is no such thing as “a certain usability”; the relative usability of a product can only be assessed having the target users in mind.

## Goals of the Usability Test

The usability test is one possible means of evaluating a product’s usability for a specified target user population; other techniques are e.g. Cognitive Walkthrough, Usability Review, or Heuristic Evaluation.

The usability test aims at getting first-hand feedback on the usage quality from the users the software product is designed for, as well as new, unthought-of design ideas. This proves extremely helpful in all instances of design decisions, at the end of the design phase, or at the end of the implementation phase, i.e. before it is actually released. It helps gathering valuable insights into possible problems and helps getting hints on how the product can be altered in order to improve the perceived quality and usage experience of a given product. Additionally, the usability test helps identifying areas of the product where things are already running smoothly, and it can help improving the user population’s perception of an implementation project by having users participate in the design.

The usability test has different goals for the two groups of people with skin in the game:

- for the test users: “The user should spend a comfortable and enjoyable day at SAP/with the SAP consultants and should take this impression on his way home.”

- for SAP: “Provide an answer to the question of whether the design of the application/the portal heads into the right direction or not.”

## Usability Test vs. Usability Review?

The usability test is not a replacement for the usability review; rather the two methods can be seen as complementary: The usability test provides some first-hand feedback on the usage quality from the users the software product is designed for, whereas the usability review deals with higher level concepts such as semantics, consistency, and meaning the users can not be aware of. The best results will be achieved if both techniques can be applied. However, in most projects the customer will only be willing to pay for one of the two techniques. In this case try to decide following these items:

- if perceived participation of the target user population has already been high (users taking part in design sessions, being informed on project process, etc.) and time is at a premium, go for a usability review.

- if you’ve got enough time and feel you need some user input on difficult questions (or if you feel some design decisions are heading in the wrong direction), try to convince the customer of the need of a usability test.

## Effort

Prices depend on the effort needed, the complexity of the object to be reviewed, and the number of roles. Basic pricing: 7 PD/L4 (one role). Each additional role: 3 PD/L4.

## Time frame

Generate user groups					Test day – 6 weeks

Invite users						Test day – 5 weeks

Create task descriptions				Test day – 2 weeks

User briefing						Test day

Usability test execution				Test day

Debriefing							Test day

Analyse, review and discuss first results	Test day + 2 days

Follow-up meetings					Test day + 1 week – 2 months

# Planning the Usability Tests

In this section you will learn how to prepare a usability test: what questions need to be answered by whom, how task descriptions should be prepared and what audience to keep in mind.

## Prerequisites

To conduct a usability test, you need the following:

- 4 test users per role from the target population: ask Product Management/Project Leader for a description of the target population (or refer to your own User Research results!)

- two User Interface Designers (one to conduct the test, ask the questions and take the notes, the other to handle the paper prototype, if applicable)

- a paper (or electronic) prototype of the product to be tested (CAVE: different roles may have different screenflows!): the prototype has to be prepared in order to allow a smooth way through the app, i.e. make notes on the back of the paper prototype’s pages on where a certain function will take you, or have the screenflow ready to stay oriented

- tasks to be performed by the test users (CAVE: different roles may have different tasks!)

- some kind of incentive for the test users (SAP mugs, money, …)

Recruit test users as early as possible. Our experience shows that getting the right test users has always proved the most demanding task.

## Kick-off meeting for the Usability Test

Sit together with the Product Management and Development Management people or the Project Leader, resp. – the project’s stakeholders have to take part in this. You need their commitment! Get answers to the following questions:

- What is ready to be tested by when?

- When will the Usability Test take place?

- Who will be invited as test users?

- How will be tested?

- Who will generate task descriptions?

- What should be the result and the audience to talk to?

## Task descriptions

Take care to get realistic task descriptions:

- task introduction: Why do users operate with this application to handle their tasks?

- choose important and frequent tasks

- word tasks goal-directedly (“You want to do something …”)

- generate independent sub-tasks – you don’t want the users to skip the rest of the test because of one unfinished task

- decide on unspecified and general task descriptions

- avoid technical (SAP) expressions and choose the users’ language

- generate reasonable and feasible tasks regarding time constraints

- place precise start and endpoints in the descriptions

- process scenarios you have observed during the Site Visits

## Audience

Always keep in mind the target audience and adapt the test’s focus to it.

- Development: Problem list with solution suggestions in combination with users’ quotes

- Product Management: Prioritized list of usability issues with user quotes and test setting descriptions; complete list of issues is optional

- Higher Management: Management summary with Top X usability issue list in combination with user quotes and test setting description; product potential description is optional

- Colleagues and other groups: Prioritized list of usability issues in combination with user quotes and test setting descriptions; description of the application (structure overview)

# Conducting the Usability Test

In this section it is described how you actually conduct a usability test. It is shown how to introduce the test users to the test situation, how to proceed during the test situation, and how to do the debriefing.

## Introduction (15’)

- Greet test users; introduce yourself and other team members; describe the role and responsibility of each member and of all devices and electronic appliances needed for the test.

- If working with video, ask the user for their written consent to be videotaped (see Appendix for a template)

- Give an overview of the proposed timeline for the usability test

- repeat again and again:

- “We want to test the software, not you!”

- “You can take a break at any time. If you want to interrupt or cancel the test, you can do so at any time!”

- “You do not have to finish all the tasks, but please try to do so!”

- If wanted, give an overview of the application, but not a detailed description. Do not give any hints on how to do something, just describe what is possible to to. Give just a high-level overview, e.g.

- “In this area you can set the objects to be shown. Here it is possible to see details of your objects”

- Ask users to complete the Questionnaire on Computer Knowledge; this comes in useful when results must be compared or related to the test users’ prior knowledge

- Plan a break of at least ten minutes between overview and test start itself: Talk to the user about general issues to distract him or her

## Test Situation (30’-60’)

- Hand out tasks; ask for comprehension problems.

- Motivate the user to “think aloud”.

- Motivate the user to tell you what s/he is seeing.

- Take notes:

- verbal utterances

- nonverbal utterances (sighing, laughter)

### Deliberately reduce user support

- If the user asks direct questions, use the following strategy:

- play dumb/stupid

- tell them to continue their task

- encourage the user to talk about his questions without giving a direct answer

- if s/he can’t continue on her/his own: provide hints and tips, but don’t give a direct answer

- Provide enough freedom to make mistakes (do not interrupt her/him immediately)

- helps you understand their goals and motivations

- gives you clues about their “fault handling and error avoidance” strategy

- Phrase open questions and avoid leading questions:

- What are you doing now?

- What do you expect to happen?

- Avoid non-verbal reactions like outcries, moans, laughs …

### Taking notes

- Take notes of anything relevant, highlight problems, e.g.

- something unexpected happens

- missing process steps, unusual order

- repetitive steps of the user (voluntary or forced)

- non-verbal reactions

- process areas or steps where the user gets lost or makes mistakes

- any context information (if the user asks for help or support)

- any valuable and interesting user quote

- Tips

- codify application area for your notes

- use abbreviations

- shorten user quotes and highlight these quotes

- Generate annotated sketches

- problem description

- possible solution proposals

- references to noted observations

## Debriefing (30’)

After the test, asks the test users about the following topics:

- General impression

- presentation of first-draft results in a high-level manner

- reassure that it is really true what you have collected

- exchange of experiences during the test regarding usability issues

- collect a plus and minus list of the tested application

- prioritisation of collected comments

- discussion on how to change the minus items

- any other things that may have come to their minds during the testing session

In case you’ve videotaped them, reassure them that the video is used for internal aims only.

Thank them and hand over the incentives, lead them to the exit.

# Analyzing the Usability Test’s Results

In this section it is shown how to proceed to gather the data from the usability test, how to make sense of the findings, and how to communicate possible suggestions for improvement.

## Gathering the data

- enter your notes into the Usability Test Report Excel sheet

- sort the notes by problem

## Making sense of the data

- identify patterns of problems

- map problems to heuristics (see 5.2.1 Usability Heuristics)

- sort problems by heuristics

- think about possible causes of the problems

- generate possible solutions to the causes

### Usability heuristics

- visibility of system status

- match between system and the real world

- user control and freedom

- consistency and standards

- error prevention

- recognition rather than recall

- flexibility and efficiency of use

- aesthetic and minimalist design

- help users recognize, diagnose, and recover from problems

- help and documentation

(Nielsen, J. (1994). Heuristic evaluation. In J. Nielsen & R. Mack (Eds.), Usability Inspection Methods. New York: John Wiley & Sons.)

## Communicating suggestions for improvement

Think about the target audiences described above when compiling your results:

- Development: Problem list with solution suggestions in combination with users’ quotes

- Product Management: Prioritized list of usability issues with user quotes and test setting descriptions; complete list of issues is optional

- Higher Management: Management summary with Top X usability issue list in combination with user quotes and test setting description; product potential description is optional

- Colleagues and other groups: Prioritized list of usability issues in combination with user quotes and test setting descriptions; description of the application (structure overview)

- Provide screenshots of the problems together with user quotes

- (Provide faked screenshots of the solutions)

- Aim at presenting at least one suggestion for change for each problematic item you’ve found

- Provide helpful change suggestions: “Change the help icon in a way users can understand it, like e.g. a Question Mark” (instead of: “Change the help icon”)

# Appendix

## Consent for video taping (English/German)

I hereby declare that I agree to my being videotaped during the usability test conducted by the SAP Portals UID consultants (names) on (date) at (place). I understand that the video will be used for SAP internal evaluation purposes; no part will be given to third parties, including my employer.

(Place, Date) (signature)

Hiermit erkläre ich mich damit einverstanden, dass ich im Rahmen des Usability Tests am (Datum) in (Ort) gefilmt werde. Der Test wird von den SAP Portals UID-Beratern (Namen) durchgeführt. Ich habe verstanden, dass die Videoaufzeichnung nur für SAP-interne Zwecke eingesetzt wird; kein Teil der Daten wird an Dritte, einschließlich meines Arbeitgebers, weitergegeben werden.

(Ort, Datum) (Unterschrift)