## Slide 1
Guidance for progression to Standard Adjusted for Comment Resolution meeting
Prepared by Vic Hayes, Chair
Lucent Technologies
Notes: 1

## Slide 2
Summary
This presentation gives the most important actions 802.11 have to take to progress its draft standard
It gives the schedule for the recirculation ballot after the January meeting to reach the June Standards Board meeting
As a back-up it gives the schedule for getting a second recirculation ballot to reach the June Standards Board meeting
Standards Board meetings in 1997:
  March 20, June 26, September 16, December 9.
Proposed standard due at IEEE office:
  Feb 7, May 16, Aug 1, Oct 31
Notes: 2

## Slide 3
What to do
At the January Comment resolution meeting we need to resolve all comment but especially those with “Do NOT Approve” votes on D5.0
Then we need to approach the “Do NOT Approve” voters and ask them if our resolution to their comments constituting their “Do NOT Approve” vote would revert their vote to an “Approve” vote
Then we need to recalculate the ballot result and list the remaining “Do NOT Approve” votes
The remaining “Do NOT Approve” votes are either:
  1) rejected by 802.11 with a rebuttal (these are for the report to the ExCom and are attached to the recirculation Sponsor ballot)
  2) unresolved (these mean 802.11 need to do more work)
Notes: 3

## Slide 4
Time Line
6
13
20
27
3
10
17
24
JAN
FEB
30
2nd recirc ballot
Plenary
FTP
Comment resolution meeting
28
5
12
19
26
7
14
21
MAY
APR
recirc ballot
3
10
17
24
31
7
14
21
MAR
APR
Teleconference?
submit
Deadline for June SAB meeting

## Slide 5
RECIRCULATION BALLOT D6.0
End of meeting Jan 17 (Fri)
Editors deliver Jan 24 (Fri) 7 days to produce
Draft on server Jan 24 (Fri)
Draft at IEEE Jan 29 (Wed)
All drafts mailed Feb 13 (Wed)
All drafts received Feb 18 (Mon)
Ballot closes Mar 4 (Tue) 19 days (39 days from server)
Meeting start Mar 10 (Mon)
Deadline May 16
SAB mtng June 24-26 Cleveland OH (Thu)
Notes: 5